## Real_Source_Records
project_id | project_name | country | state | project_type | road_length_km | estimated_cost_usd_m | adb_loan_usd_m | counterpart_usd_m | planned_duration_years | original_closing | revised_closing | actual_closing | land_acquisition_resettlement_usd_m | land_acquisition_issue | land_acquisition_note | source_type | source_url | revised_to_actual_delay_months | original_to_actual_delay_months | cost_counterpart_check_usd_m
41629-013/44425-013 | Bihar State Highways II Project and Additional Financing | India | Bihar | State highways | 356 | 424 | 300 | 124.7 | 4 | 2014-12-31 |  |  | 78.93 | 1 | ADB PCR recommendation: about 50% of land should be acquired by loan negotiations; contracts should be awarded only after substantial acquisition. | ADB Project Completion Report + ADB RRP/PDS | https://www.adb.org/sites/default/files/project-documents/41629/41629-013-44425-013-pcr-en.pdf |  |  | 424.7
35335-013 | National Highway Sector II | India | Multiple/India | National highways | 566 | 670.6 | 400 | 270.6 | 4 | 2008-12-31 | 2011-12-31 | 2012-05-09 |  |  |  | ADB Project Data Sheet + Completion Report listing | https://www.adb.org/projects/35335-013/main | 4.27 | 40.25 | 670.6
37328-013 | Madhya Pradesh State Roads Sector Project II | India | Madhya Pradesh | State roads | 1800 | 400 | 320 | 80 | 3.58 | 2010-12-31 | 2011-12-31 | 2012-10-05 |  |  | ADB project page lists involuntary resettlement as not applicable. | ADB Project Data Sheet + Completion Report listing | https://www.adb.org/projects/37328-013/main | 9.17 | 21.16 | 400
42513-013 | Karnataka State Highway Improvement Project | India | Karnataka | State highways | 615 | 452.75 | 305 | 147.75 | 4 | 2015-06-30 | 2018-10-31 | 2019-04-23 |  |  | Safeguard category: involuntary resettlement A. | ADB Project Data Sheet + Completion Report listing | https://www.adb.org/projects/42513-013/main | 5.72 | 45.77 | 452.75
47270-001 | Madhya Pradesh District Connectivity Sector Project | India | Madhya Pradesh | District roads | 1600 | 500 | 350 | 150 | 3.67 | 2018-10-31 |  | 2019-03-28 |  |  | Safeguard category: involuntary resettlement B. All 18 civil works contracts were awarded in 2014–2015. | ADB Project Data Sheet + Completion Report listing | https://www.adb.org/projects/47270-001/main |  | 4.86 | 500
37143-033 | North Eastern States Roads Investment Program (Project 2) | India | Assam/Manipur/Mizoram/Tripura | State roads |  | 157.2 | 125.2 | 32 | [7 empty] | ADB project data sheet (archived indexed copy) + ADB project page | https://www.adb.org/projects/37143-033/main |  |  | 157.2
32203-013 | West Bengal Corridor Development Project | India | West Bengal | State highways / rural roads | 240 |  | 148.7 | [8 empty] | ADB project page + Government of India/MoRTH historical record | https://www.adb.org/projects/32203-013/main
49228-002 | Rajasthan State Highway Investment Program - Tranche 1 | India | Rajasthan | State highways / MDR | 1000 | [10 empty] | ADB project page + completion report listing | https://www.adb.org/projects/49228-002/main

## Data_Dictionary
field | type | provenance | definition
project_id | string | Real | ADB project identifier
project_name | string | Real | Project title
state | categorical | Real/derived | State or multi-state coverage
project_type | categorical | Real | Transport/project category
road_length_km | numeric | Real | Reported project road length where available
estimated_cost_usd_m | numeric | Real | Appraisal/total project cost where available
adb_loan_usd_m | numeric | Real | ADB financing
counterpart_usd_m | numeric | Real | Government/counterpart financing
planned_duration_years | numeric | Real/derived | Only when source gives implementation period
original_closing | date | Real | Original loan/project closing
revised_closing | date | Real | Revised closing
actual_closing | date | Real | Actual closing
land_acquisition_resettlement_usd_m | numeric | Real | Reported LA/R&R budget where available
land_acquisition_issue | binary | Real/text-derived | Only mark 1 when source explicitly supports it
land_acquisition_note | text | Real/text-derived | Evidence/qualitative finding
revised_to_actual_delay_months | numeric | Derived | (Actual closing - revised closing) in months
original_to_actual_delay_months | numeric | Derived | (Actual closing - original closing) in months
time_overrun_pct | numeric | Derived | 100*(actual implementation duration-planned duration)/planned duration; requires comparable start/end dates
cost_overrun_pct | numeric | Derived | 100*(actual cost-estimated cost)/estimated cost; requires actual completion cost
source_url | URL | Real | Official/source record URL

## Formulas
Formula | Expression | Use
Time overrun % | 100*(actual duration-planned duration)/planned duration | Only if start/end dates are comparable
Cost overrun % | 100*(actual cost-estimated cost)/estimated cost | Only if both costs are comparable
Acquisition completion % | 100*land acquired/land required | Land-acquisition source required
Compensation paid % | 100*compensation paid/compensation required | Land-acquisition source required
Logistic regression | P(delay)=1/(1+e^(-z)); z=β0+ΣβiXi | Baseline classifier
Linear regression | y=β0+ΣβiXi+ε | Baseline regression
RII | ΣW/(A*N) | A=5 for a 5-point Likert survey
Legal intensity | pending legal cases/(affected parcels+1) | Derived feature if fields exist

## References
Source | Relevance | URL
Andrić et al. 2025 | 138 completed South Asian projects; 83 India; delay causes; linear/quadratic/Random Forest | https://www.sciencedirect.com/science/article/pii/S1226798825003241
Andrić et al. 2024 | Same 138-project database; 108 ADB + 30 MoSPI | https://www.mdpi.com/2071-1050/16/24/11159
MoSPI PAIMANA | Indian project monitoring / schedule and cost slippage causes | https://paimana-proj.mospi.gov.in/
MoSPI public dashboard | Project-monitoring dashboard | https://ipm.mospi.gov.in/Home/PublicDashboard
Devi & Sindhu 2025 | India delay factors, RII/PCA; land acquisition in road projects | https://link.springer.com/article/10.1007/s40030-025-00899-5